Work Breakdown Structure (WBS)

Disaster Relief Supply & Volunteer Coordinator | Problem Statement #64 | [Your Name], [Your SRN], [Section] Section

The project is split into six work packages. Effort is in person-days and is an estimate for one student. Phases follow the usual order: requirements, design, implementation, testing, deployment.

| WBS ID | Task | Deliverable | Effort (days) |
| --- | --- | --- | --- |
| 1 | Project Initiation |  |  |
| 1.1 | Study problem statement #64 | Understanding notes | 0.5 |
| 1.2 | Create GitHub repository and Jira project | Repo + Jira board | 0.5 |
| 2 | Requirements Engineering |  |  |
| 2.1 | Write 5 FR and 2 NFR | Requirements table | 1 |
| 2.2 | Draw UML use-case diagram | UML diagram | 1 |
| 2.3 | Write use-case flow specification | Flow spec (1 page) | 0.5 |
| 2.4 | Prepare RTM | RTM document | 0.5 |
| 2.5 | Write SRS | SRS document | 2 |
| 3 | Design |  |  |
| 3.1 | Architecture diagram | Architecture diagram | 1 |
| 3.2 | Database schema (PostgreSQL / PostGIS) | Schema design | 1 |
| 3.3 | REST API design | API list | 1 |
| 3.4 | UI wireframes (dashboard, requisition form, offline states) | Wireframes | 1.5 |
| 4 | Implementation |  |  |
| 4.1 | Authentication, roles and user verification (NFR-002) | Auth module | 2 |
| 4.2 | Requisition and priority engine (UC-01) | Requisition module | 1.5 |
| 4.3 | Allocation, warehouse stock and shortfall (UC-02, UC-03, UC-04) | Allocation module | 2.5 |
| 4.4 | Volunteer profile and skill-based dispatch (UC-05, UC-06, UC-07, UC-12) | Dispatch module | 2.5 |
| 4.5 | Delivery tracking, GPS feed and delay alerts (UC-08, UC-09, UC-10) | Tracking module | 2.5 |
| 4.6 | Offline GIS cache and sync (NFR-001) | Offline / sync module | 2.5 |
| 4.7 | Situation map and report (UC-11) | Reporting module | 2 |
| 5 | Testing |  |  |
| 5.1 | Test plan and test cases | Test plan | 1 |
| 5.2 | Unit tests | Unit test results | 2 |
| 5.3 | Integration and system tests | Test report | 2 |
| 5.4 | Performance (256 kbps, offline) and security tests (NFR-001, NFR-002) | Benchmark report | 1.5 |
| 5.5 | Bug fix and retest using AI-assisted coding | Fixed code + repo link | 1 |
| 6 | Deployment and Documentation |  |  |
| 6.1 | Deployment and environment setup notes | Deployment steps | 1 |
| 6.2 | README, screenshots and demo | README + demo | 1 |
| 6.3 | Final review and submission | Submitted repo | 0.5 |

Total estimated effort: 36 person-days.

Dependencies: Design (3) needs Requirements (2). Implementation (4) needs Design (3). Testing (5) needs Implementation (4). Deployment (6) needs Testing (5).